SCHEDULE OF EVENTS

| Date Start Time End Time | ### Description / Room | Set Up |
| --- | --- | --- |
| 1/17/2002 (Thursday) 06:00 PM-11:59 PM | Small Events Terrace Room | No setup required for loadin. Stage to be totally cleared and cleaned. |
| 1/17/2002 (Thursday) 12:00 PM-8:59 PM | Main Events Setup Imperial Ballroom | Room Clean and Empty. (10) Easels. No other setup required for Loadin. |
| 1/17/2002 (Thursday) 9:00 PM-11:59 PM | Main Events Setup Imperial Ballroom | Air wall to Plaza closed. (3) 24” Risers for video. (2) 12” risers for sound/lighting, One table on each riser. See staff there for exact locations. Tables NOT skirted or covered. Water setups, (2) trash bins. |
| 1/17/2002 (Thursday) 12:00 PM-11:59 PM | Hancock Room | (5) 6ftx36 skirted with (10) chairs, Water setup Several large trash bins. (3) easels. (1) comfy couch. |

| 1/18/2002 (Friday) 08:00 AM – 7:30 PM | Main Events Setup Imperial Ballroom | Existing set |
| --- | --- | --- |
| 1/18/2002 (Friday) 08:00 AM – 7:30 PM | Small Events Setup Terrace Room NERO | Max seating on terrace levels (2) skirted 6xl8” tables on stage with Clear center depressed area. Chairs for ½ max seating on Terrace level. (2) trash bins |
| 1/18/2002 (Friday) 8:00 PM-10:30 PM | Panel. Terrace Room | Theatre style, (2) skirted tables in front with (5) chairs behind tables. (1) water setup in room |
| 1/18/2002 (Friday) 10:30 PM-8:00 AM (Sat) | Small Events Setup Terrace Room Drum Circle | (30) chairs in circle in center depressed area. (50) additional chairs in room. |
| 1/18/2002 (Friday) 08:00 PM-11:59 PM | Period Dance Imperial Ballroom | (10) Round tables, (100) chairs. Chairs and tables along side wall under balconies. Water setups along edges of room. Refresh water every hour. (Double the usual number of water setups.) Dance floor. (Leave uncovered all weekend.) (1) Easel. Banquet order: See Depart info for details. |
| 1/18/2002 (Friday) 08:00 PM-11:59 PM | Small Events Setup Hancock Room Dance Dance Revolution | (1) skirted 6’x18” table at front of room with (4) chairs (20) additional chairs along walls (1) water setup at front of room, refreshed every 2 hours |

| 1/18/2002 (Saturday) 12:00 AM-4:00 AM | Scissorskiss Imperial Ballroom | Existing set. Please continue to refresh water setups. |
| --- | --- | --- |
| 1/19/2002 (Saturday) 08:00 AM-2:00 PM | Scrapheap Challenge Imperial Ballroom | (6) 6’x18” tables NOT skirted centered in back half of room. (200) Chairs Theater Style in back of room. (1) small table skirted (2) water setups. |
| 1/19/2002 (Saturday) 10:00 AM-11:30 AM | Higgin’s Armory Terrace Room | Reset to Theatre |
| 1/19/2002 (Saturday) 11:30 AM-1:00 PM | WGOH Reading Terrace Room | Existing Set. |
| 1/19/2002 (Saturday) 1:00 PM-2:00 PM | Pettinger Slide Show Terrace Room | Existing Set. |
| 1/19/2002 (Saturday) 2:00 PM-3:00 PM | Filk Concert Terrace Room | Existing Set. |
| 1/19/2002 (Saturday) 3:00 AM-4:00 PM | WGOH/FGOH Interview Terrace Room | Existing Set. |
| 1/19/2002 (Saturday) 4:00 AM-5:00 PM | AGOH Slideshow Terrace Room | Existing Set. |
| 1/19/2002 (Saturday) 05:30 PM-06:30 PM | ATAAC Sword Demo Terrace Room | Max seating on terrace levels (2) skirted 6xl8” tables on stage with Clear center depressed area. Chairs for ½ max seating on Terrace level. (2) trash bins |
| CONTINUE FROM HERE!!!! |  |  |
| 1/19/2002 (Saturday) 08:00 PM-08:00 AM | Rocky Horror. Terrace Room | Theatre seating along sides facing center of room. Seats in lower level along edge. Center of room open. Water setups on balcony. |
| 1/19/2002 (Saturday) 12:01 PM-11:59 PM | Fan Table Area 2nd Floor Mezzanine | Existing Set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Information 2nd Floor Mezzanine near Dartmouth | Existing Set |
| 1/19/2002 (Saturday) 12:01 AM-09:OOAM | Main Events Setup Imperial Ballroom | Existing Set Please add the “Wedding Chairs” to the room. |
| 1/19/2002 (Saturday) 11:00 AM-12:45 PM | GOH Interview Imperial Ballroom | Existing set |
| 1/19/2002 (Saturday) 01:00 PM-3:00 PM | GOH Reading Imperial Ballroom | Theater seating in front ½ of ballroom. NOTE: Previous event ends at 12:45 PM. HOTEL WILL ONLY HAVE FIFTEEN MINUTES TO RESET ROOM!!! |
| 01/19/2002 (Saturday) 03:00 PM-07:00 PM | Masquerade Rehearsal Imperial Ballroom | Theatre style MAX seating added to original Thursday setup during this period Extra water setups along walls. SWEEP and MOP kitchen and stage Area leading from B/C to stage. |
| 1/19/2002 (Saturday) 07:00 PM-11:00 PM | Masquerade Imperial Ballroom | Existing set |
| 1/19/2002 (Saturday) 12:00 Midnight-08:00 AM (All night) | Club Dance Imperial Ballroom | Chairs along walls. Dance floor in center of Room. Round tables with chairs around dance Floor Water setups along edges of room. Refresh water every hour. (Double the usual number of water setups.) |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Dealer’s Room Plaza Ballroom | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Registration Stanboro Coat Room | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Registration Stanboro Coat Room Foyer (outside Convention Services Office) | Existing set. |
| 1/19/2002 (Saturday) 10:00 AM-11:59 PM | Gaming Stanboro | Existing set. Water setups refreshed every hour during day. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Conference Operations, Headquarters, Security Hancock Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Gopher Hole Fairfield Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Office Exeter Room | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Sales Office Dartmouth Room (storage closet) | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-3:00 PM | Film Room Berkeley Room | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-3:00 PM | Film Room Clarendon Room | Existing set |
| 1/19/2002 (Saturday) 03:00 PM-05:00 PM | Art GOH Slide Show Berkeley and Clarendon Room | Existing set |
| 1/19/2002 (Saturday) 05:30 PM-11:00 PM | Masquerade Green Rm. Berkeley Room | Air wall to Clarendon open, Air wall to Arlington Closed. (6) 6’x18” tables, (50) chairs arranged around room perimeter, (4) water setups refreshed once each hour. (2) large trash bins Stack extra chairs against wall. NOTE: Previous event ends at 05:15 PM. HOTEL WILL ONLY HAVE FIFTEEN MINUTES TO RESET ROOM!!! |
| 1/19/2002 (Saturday) 05:30 PM-11:00 PM | Masquerade Green Rm. Clarendon Room | Air wall to Berkeley open. Put comfy chairs, Couches, and regular chairs against wall. |
| 1/19/2002 (Saturday) 11:00 PM-11:59 PM | Film room Berkeley Room | Return room to theatre setup FACING OTHER DIRECTION (chairs FACING Georgian). NOTE: Actual time previous event ends and New event starts is variable. On duty manager Will advise. Time will be critical, HOTEL WILL HAVE ONLY FIFTEEN MINUTES TO RESET ROOM!!! |
| 1/19/2002 (Saturday) 11:00 PM-11:59 PM | Film Room Clarendon Room | Return room to theatre setup as per Berkeley. Air wall to Berkeley open. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Art Show Georgian Room | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Art Show Arlington Room | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Film/Video Storage Georgian Coat Room | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Information 4th floor elevator lobby | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Programming Winthrop Room | Existing set |
| 1/19/2002 (Saturday) 09:00 AM-11:59 PM | Programming Whittier Room | Theatre style, (2) skirted tables at front with (2) chairs each. Water setup along wall. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | Programming White Hill Room | Existing set. |
| 1/19/2002 (Saturday) 05:00 AM-11:59 PM | Programming St. James Room | Theatre style, (2) skirted tables in front with (5) chairs behind tables. (35) chairs arranged around side of room (1) water setup in each room, refreshed every 2 hours. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | Programming Thoreau Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | Programming Tremont Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-2:00 AM | Costume Programming Stuart Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | DivHead and Eboard Mtg. Stanhope Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Programming Statler Room | Existing set |
| 1/19/2002 (Saturday) 12:01 AM-1i:59 PM | Program Operations. Shawmut Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | Programming Lenox Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Programming Longfellow Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-i 1:59 PM | Programming Holmes Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-i 1:59 PM | Programming Gloucester Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-i 1:59 PM | Programming Emerson Room | Theatre style, (2) skirted tables in front with (5) chairs behind tables. (1) water setup in each room, refreshed every 2 hours.. Bathroom unlocked. |
| 1/19/2002 (Saturday) 12:01 AM-06:00 AM | Programming Franklin Room | Existing set. |
| 1/19/2002 (Saturday) 06:00 AM-11:59 PM | Programming Franklin Room | (1) skirted table at end of room Middle of room clear (35) chairs arranged around side of room (1) water setup in each room, refreshed every 2 hours. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | LARP (Role Play Game) Constitution Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Newsletter, Sign Shop Board Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | LARP Charles River Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM- 11:59 PM | Video Theatre Cambridge Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | LARP Cabot Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Anime Theatre Beacon Hill Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | Programming Brandeis Room | Existing set. |
| 1/19/2002 (Saturday) 12:01 AM-11:59 PM | Programming Alcott Room | Existing set. |
| 1/19/2002 (Saturday) 09:00 AM-09:00 PM | Programming Back Bay Room | (6) round tables with (40) chairs. Water setups on each table. |

| 1/20/2002 (Sunday) 10:00 AM- 12:00 PM |  |  |
| --- | --- | --- |
| 1/20/2002 (Sunday) 01:00 PM-04:00 PM | Sunday Sundae. Terrace Room | Clear chairs from lower level except at edge. Round tables on balcony with chairs. (2) water setups. Ice Cream banquet function. For serving: (2) sets each of ice cream stations consiting of 2 rows of (3) 6x30 tables (2) topping stations (1) 6x30 table each (8) 6x30 tables in main floor This setup is to aid in traffic flow throughout duration of social. |
| 1/20/2002 (Sunday) 06:00 AM-11:59 PM | Fan Table Area 2nd Floor Mezzanine | (10) skirted tables arranged around Mezzanine railing overlooking lobby starting from elevators going along railing, around corner and ending at Hancock Room area. (2) 6x30 skirted tables near former Dartmouth Room door, (2) 6x30 tables along railing at top of stairs near corridor leading down to Arlington/Berkeley rooms. (2) trash bins in A/B corridor area. |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Information 2nd Floor Mezzanine near Dartmouth | Existing set |
| 1/20/2002 (Sunday) 10:00 AM-12:00 Noon | NERO Imperial Ballroom | Chairs along walls. Dance floor in center of Room. Round tables with chairs around dance Floor Water setups along edges of room. Refresh water every hour. (Double the usual number of water setups.) |
| 1/20/2002 (Sunday) 01:00 PM-11:59 PM | Teardown/Loadout Imperial Ballroom | Room empty for teardown. Water setups along walls. (4) tables, not skirted, and (8) chairs only |
| 1/20/2002 (Sunday) 12:01 AM-08:00 PM | Dealer’s Room Plaza Ballroom | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Registration Stanboro Coat Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-06:00 PM | Registration Stanboro Coat Room Foyer (outside Convention Service office) | Existing set |
| 1/20/2002 (Sunday) 10:00 AM-08:00 PM | Gaming Stanboro Room | Existing set. Water refreshed every 2 hours. |
| 1/20/2002 (Sunday) 12:01 AM-06:00 PM | Conference Operations, Headquarters, Security Hancock Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-06:00 PM | Gopher Hole Fairfield Room | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-10:00 PM | Office Exeter Room | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Sales Office Dartmouth Room (storage closet) | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-12:30 PM | Film Room Berkeley Room | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-12:30 PM | Film Room Clarendon Room | Existing set. |
| 1/20/2002 (Sunday) 12:30 PM-06:00 PM | Art Show Auction Berkeley Room | Existing set. |
| 1/20/2002 (Sunday) 12:45 PM-06:00 PM | Art Show Auction Clarendon Room | Remove comfy furniture, replace with regular chairs in theatre style. (6) 6’x18’ tables at front of room. (1) water setup at room front. (1) 8-step ladder delivered. NOTE: HOTEL WILL ONLY HAVE 15 MINUTES TO RESET |
| 1/20/2002 (Sunday) 12:01 AM-09:00 PM | Art Show Georgian Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-12:00 Noon | Art Show Arlington Room | Existing set |
| 1/20/2002 (Sunday) 12:30 PM-09:00 PM | Art Show Arlington Room | Remove round tables. (12) 6x18 tables setup as per Attachment C. (12) chairs. |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Film/Video Storage Georgian Coat Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-06:00 PM | Information 4th floor elevator lobby | Existing set. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming Winthrop Room | Existing set |
| 1/20/2002 (Sunday) 09:00 AM-06:00 PM | Programming Whittier Room | Existing set |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming White Hill Room | Existing set. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming St. James Room | Theatre style, (2) skirted tables in front with (5) chairs behind tables. (35) chairs arranged around side of room (1) water setup in each room, refreshed every 2 hours. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming Thoreau Room | Existing set. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming Tremont Room | Theatre style. (1) water setup in room, refreshed every 2 hours. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Costume Programming Stuart Room | Existing set |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | DivHead and Eboard Mtgs. Stanhope Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-06:00 PM | Programming Statler Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Program Operations Shawmut Room | Existing set |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming Lenox Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-06:00 PM | Programming Longfellow Room | Existing set |
| 1/20/2002 (Sunday) 09:00 AM-06:00 PM | Programming Holmes Room | Existing set |
| 1/20/2002 (Sunday) 09:00 AM-06:00 PM | Programming Gloucester Room | Existing set |
| 1/20/2002 (Sunday) 09:00 AM-06:00 PM | Programming Emerson Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-06:00 AM | Programming Franklin Room | Existing set |
| 1/20/2002 (Sunday) 12:01 AM-06:00 PM | LARP (Role Play Game) Constitution Room | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Newsletter, Sign Shop Board Room | Existing set. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | LARP Charles River Room | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Video Theatre Cambridge Room | Existing set. |
| 1/20/2002 (Sunday) 06:00 AM-11:59 PM | Programming Franklin Room | Theatre style, (2) skirted tables in front with (5) chairs behind tables. (1) water setup in each room, refreshed every 2 hours. |
| 1/20/2002 (Sunday) 09:00 AM-06:00 PM | LARP Cabot Room | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Anime Theatre Beacon Hill Room | Existing set. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming Brandeis Room | Existing set. |
| 1/20/2002 (Sunday) 12:01 AM-11:59 PM | Programming Alcott Room | Existing set. |
| 1/20/2002 (Sunday) 09:00 AM-04:00 PM | Programming Back Bay Room | (6) round tables with (40) chairs. Water setups on each table. |

| 1/21/2002 (Monday) 12:01 AM-11:59 PM | Storage Stanboro Coat Room | Existing set. |
| --- | --- | --- |
| 1/21/2002 (Monday) 12:01 AM-11:59 PM | Storage Georgian Coat Room | Existing set. |
| 1/21/2002 (Monday) 12:01 AM-11:59 PM | Storage Dartmouth Room (Storage closet) | Existing set. |
| 1/21/2002 (Monday) 12:01 AM-11:59 PM | Conference Operations, Headquarters, Security Hancock Room | Existing set. |
| 1/21/2002 (Monday) 12:01 AM-06:00 PM | Office/Teardown Stanboro Room | No setup needed. |
| 1/22/2002 (Tuesday) 12:01 AM-i 2:00 Noon | Storage Stanboro Coat Room | No setup needed. |
| 1/22/2002 (Tuesday) 12:01 AM-12:00 Noon | Storage Georgian Coat Room | No setup needed. |

#### END OF CONFERENCE