FOGcon Coordinator & Convention Timeline (adapted from WisCon)

| Approximate Time | Action |
| --- | --- |
| Starting as soon as you accept the coordinator job | Recruit ConCom staff. Start with incumbents to see who is willing to continue in their current role for another year. Recruit for vacant positions until all are filled (this may take months). |
| Starting as soon as you accept the coordinator job | Start recruiting your successor(s). Continue this effort until at least one candidate is in place. |
| During the current year’s con | Programming should open the idea-collecting database for next year’s con, and should announce same via newsletter, website and emails to their list of prior contacts. |
| Shortly post-con | Set your meeting schedule, and post it on the calendar on the Google ConCom site. (Keep dates of hardcopy progress reports in mind.) Also schedule GoH nomination and voting periods. |
| Mid March to early April | Wrap-up meeting for prior convention; incoming coordinator attends, and takes over moderating once the discussion moves to the future convention. |
| Late March | The first newsletter for the following year’s convention should go out at about this point. |
| March or April | Meeting with hotel staff and hotel liaison to discuss just-completed event and any changes or improvements needed for following year. |
| Spring | Programming kick-off meeting. |
| Late Spring/early Summer | Review your ConCom list and send confirmation emails to all the individuals with whom you have not personally spoken since the prior convention. Invite any who are not yet on the ConCom list on Google to join the group. |
| June or July | If newsletter 2 has not yet gone out, this would be a good time to send it. |
| June or July | Stamp, sticker & mail out the first hardcopy notice if applicable. |
| August | Begin reviewing the prior year’s big hardcopy progress report for needed changes and updates. Start a list of committees that will need to submit text for the new one. Check with SF3 officers to determine whether this should go out first class or bulk mail. |
| August | Your hotel liaisons should have the overflow hotel block set up by now (possibly sooner, depending on pickup rates at Concourse, but no later). |
| September | If a third newsletter has not yet gone out, this would be a good time to send it. |
| September | Work with publications chair to finalize the October progress report. |
| October | Establish the scholarship committee |
| October | Stamp, sticker & mail out the second hardcopy progress report. |
| Mid-October | Dealers' Room applications due; process of deciding who to accept begins. |
| Mid-October | If you have not identified at least one potential successor coordinator, start considering delaying the guest of honor selection until a candidate is in place. |
| Mid-late October | If newsletter 4 has not yet gone out, this would be a good time to send it. |
| Mid-late October | Programming idea collection should close. |
| Late October to late November | Open Guest of Honor nominations for following year’s FOGcon. Announce this by eCube and on the website. Accept nominations for approximately two weeks. |
| Two weeks after opening GoH nominations | Close nominations and develop GoH ballot. Email ballot and supporting paragraphs to all active ConCom members. Accept ballots for two weeks. |
| Two weeks after voting starts | Close the ballot acceptance window and tabulate the results. Contact top two vote-getters to extend the invitation. Upon acceptance, announce names to ConCom (but NOT in newsletter or on website). |
| Late December-early January | Start negotiations for future hotel rates. |
| Late December-early January | Start process of establishing FOGcon rates for following year. |
| Late December-early January | Party coordinator works with hotel liaison and programming to finalize party schedule. |
| By the end of December | Scholarships awarded and details communicated to the treasurer. |
| December through February | Newsletter releases as needed. |
| December | If recruiting a sister organization to provide Opening Ceremonies entertainment, start contacting them now. Follow up regularly. |
| Late December | Start planning content of final Progress Report, obtaining updates as needed. |
| January | Contact cab company about cab vouchers. |
| January | Contact Send It Now about shipping services. |
| January | If offering a reduced-rate car rental package, contact the desired car rental provider to set it up. |
| January | Hotel liaisons should be working on non-programming room setups. |
| Mid-late January | Contact any sister organizations who will be presenting awards at the convention to coordinate plans for Sunday evening event. |
| Mid-late January | Start working with stage manager(s) on plans for opening ceremonies and guest of honor speeches and awards. |
| Mid-late January | Start work on post-con survey questions. |
| Mid-late January | Start reviewing pocket program text (non-programming portion) for needed updates. |
| Late January | Hotel liaisons should be working on programming room setups. |
| Late January | Send out prior year’s survey questions to all department heads so they can tweak/adjust for the current convention. Set a deadline of mid-February for responses. |
| Late January-early February | Program downloads for pocket program to pubs chair. |
| Late January-early February | Hotel liaisons should arrange for bagging 2 parking meters for logistics truck. OR, logistics coordinator should contract with movers for load in/load out. |
| Early February (or when 1,000 members register) | Progress Report #3 stickered, stamped & mailed. |
| Early February (or when 1,000 members register) | Pre-con reg transfers database to at-con reg for preparation of name badges & packet labels. |
| Throughout February | Make decisions about wait-listers and any requests to exceed the cap |
| Early February | At-con reg interfaces with database admin to develop badge-back labels for program participants. NOTE: obsolete with new database |
| Early February | Start assembling lists (keys, lanyards, ConCom, special badges, cell phone numbers). |
| Early-mid February at latest | Set date for wrap-up meeting, announce to ConCom. |
| Mid-February | Survey questions should be finalized, either Coordinator or a designated assistant should start setting it up on SurveyMonkey. |
| Wednesday afternoon before con | Hotel meeting with hotel staff, hotel liaisons, safety, department heads. |
| Wednesday evening before con | Packet-stickering party. NOTE: obsolete with new database |
| Thursday morning before con | Logistics loads in all supplies from [local] storage locker and other points in and around San Francisco, OR meets movers and oversees their efforts to move all supplies to hotel |
| Thursday afternoon before con | Setup begins. |
| Thursday before con | Packet stuffing. NOTE: obsolete with new database |
| Friday morning of con | On-line survey should be ready absolutely no later than this point. |
| Monday afternoon | Post-Mortem panel: use this to both gather ideas for the future and to educate members who make unrealistic suggestions (expect plenty of those) |
| Monday afternoon | Teardown begins. Logistics gathers all supplies together in a single room (or two) at hotel. |
| Tuesday morning | Logistics returns all supplies to storage locker (or other locations). |
| Within 1 week after con | Distribute Post-Mortem panel notes to appropriate ConCom members. |
| 3-6 weeks after con | Wrap-up meeting, official handoff to new coordinator(s). |